## Article Tracking - MASTER
Meeting / Initiative | Article # | Article Title / Project | Value | Description | Department | Status | Date Updated
STM 2023 | 6 | Fund Economic And Environmental Initiatives | 200000 | $200,000.00 for the purpose of funding electric vehicle charging stations, hydration stations, solar waste receptacles, and related initiatives to be placed on Town-owned property, at various locations including all costs. | Town Manager | The environment plays a vital role in the economy of our community. Funding opportunities for these types of projects, such as grants or cost offsets from utility companies have funding cycles and commitment deadlines that do not always align with our fiscal year or town meeting schedule. This article provides a funding source for projects or funding to use as a match to pursue grants or other funding opportunities as they arise. For example, the Town is currently considering the installation of four dualport charging stations at an estimated cost of $120,000. These costs will likely be offset by a utility company, but the exact amount of the offset versus cost to the town is unknown until the project completes the approval process. | 2024-11-01
STM 2023 | 8 | Fund Design Of Solar Project At The Water Treatment Plant | 25000 | $25,000.00 for the purpose of funding conceptual design services for a solar project at the Water Treatment Plant. | Department of Public Works | RFP for proposals for solar construction later in 2025. | 2025-06-27
STM 2023 | 12 | Fund Human Resources Staffing & Related Expenses | 150000 | The Town does not currently have a position dedicated to the Town’s Human Resources. The complexity of staffing and legal issues combined with the sheer volume of hiring, require that an executive position be created. The article funds one full-time employee with benefits. | Town Manager | Human Resources Director hired January 2025. | 2025-01-15
STM 2023 | 13 | Fund Recreation Department Staffing & Related Operational Expenses | 168000 | $168,000.00 to fund costs for additional staffing, and related operational expenses for the Recreation Department. | Recreation | The additional Full-Time staff member has been a huge help with the day-to-day operations of the Orleans Recreation, Culture & Community Events Department. We have now been able to assist residents and organizations with the preparation and execution of their events. We are excited for the adult based programming to come. | 2025-06-20
STM 2023 | 15 | Comprehensive Plan Update | 120000 | $120,000.00 for the purpose of updating the Town’s Comprehensive Plan. | Planning and Community Development | Outreach to boards & committees completed, full draft plan expected late June. Public engagement scheduled for summer. Possible Fall TM Article to adopt. | 2025-06-23
STM 2023 | 16 | Fund Awareness And Educational Initiatives To Honor Indigenous Peoples | 15000 | $15,000.00 to fund costs associated with awareness and educational initiatives to honor Indigenous Peoples. | Town Manager | Select Board Meeting preamble, read before every meeting: "We acknowledge, with respect, that we are inhabiting the traditional lands of the Nauset and Wôpanâak (Wampanoag) peoples who have always existed here. We value their roles as past, present, and future guardians of this land." Further, this article provides funding to begin outreach through awareness and educational initiatives. Relates to FY24 Select Board Goal #9. NRMS Wetu Project discussed with Select Board September 2024. | 2024-11-01
STM 2023 | 18 | Funding For The Special Education Stabilization Fund | 52000 | $52,000.00 (Free Cash) to the Special Education Stabilization Fund. | Town Manager | This article provides initial funding for the new Special Education Stabilization Fund. | 2024-11-01
STM 2023 | 24 | Home Rule Petition for a Pesticide Reduction Bylaw | - | The article authorizes the Select Board to file special legislation authorizing the adoption of the proposed bylaw as the application of pesticides in Orleans is currently primarily regulated by state and federal law. This article also proposes the adoption of a bylaw that seeks to reduce toxic pesticide use in and on public and private property in order to promote a healthy environment and to protect the public from the hazards of pesticide use. It does not prohibit businesses from selling products containing pesticides to anyone. | Town Manager | The article authorizes the Select Board to file special legislation authorizing the adoption of the proposed bylaw as the application of pesticides in Orleans is currently primarily regulated by state and federal law. This article also proposes the adoption of a bylaw that seeks to reduce toxic pesticide use in and on public and private property in order to promote a healthy environment and to protect the public from the hazards of pesticide use. It does not prohibit businesses from selling products containing pesticides to anyone. See Pesticide Home Rule Petition 2023 below. | 2024-11-01
ATM 2024 | 15 | Fund CPA Program Budget | 1379441 | To see if the Town will vote to act on the report of the Community Preservation Committee on the Fiscal Year 2025 Community Preservation budget and to appropriate or reserve for later appropriation monies from the Community Preservation Fund's Annual Revenues and/or available funds for the payment of debt service, undertaking of Community Preservation projects, the Administrative Expenses of the Community Preservation 27 Committee and all other necessary and proper expenses for FY25, or to take any other action relative thereto. (Community Preservation Committee) | Community Preservation Committee | Nine projects have successfully completed and four are ongoing. Several completed projects came in slightly underbudget. $29,800 was returned to the CPC accounts at the close of the financial year. | 2025-06-24
ATM 2024 | 17 | Fund Rock Harbor Commercial Wharf Improvements | 9000000 | $9,000,000.00 to fund the Rock Harbor Commercial Wharf Improvements Project, including all expenses. | Department of Public Works | Construction is ongoing with tentative completion date of 12/30/2025 | 2025-06-27
ATM 2024 | 18 | Comprehensive Water Resources Management Plan Implementation Phase III Lakes & Ponds Sewer Study Area Design | 1200000 | $1,200,000 be appropriated for this purpose and for costs incidental and related thereto, and that the Treasurer, with approval of the Select Board, is authorized to borrow the sum of $1,200,000 pursuant to Massachusetts General Laws, Chapter 44 Sec. 7 and 8, or any other enabling authority, and to issue bonds or notes of the Town therefore, provided however that this vote shall not take effect until the Town votes to exempt from the limitations on total taxes imposed by the Massachusetts General Laws Chapter 59, Section 21C (Proposition 2 ½ so-called) the amounts required to pay the principal and interest on the borrowing approved by such vote. Explanation: This article will fund the continued implementation of the Town’s Amended Comprehensive Water Quality Management Plan activities for FY25. The project includes the final design related to the Phase III – Lakes and Ponds Sewer Study Area (see map in appendix) | Department of Public Works | We are currently in the 60% design phase working our way towards 100%. An official application is being prepared to secure SRF financing with an application deadline in October 2025. | 2025-06-27
ATM 2024 | 19 | Comprehensive Water Resources Management Plan Implementation Phase II Meetinghouse Pond Area Expansion | - | Amend the action taken under Article 19 of the May 9, 2022 Annual Town Meeting warrant and Article 27 of the October 16, 2023 Special Town Meeting warrant to expand the Phase II Meetinghouse Pond Area Collection System and Pumping Station Project to include the additional 28 properties. | Department of Public Works | Project is on hold at this time as SRF financing was not available to the Town. | 2025-06-27
ATM 2024 | 28 | Fund Water Quality Testing | 261074 | Town programs to protect and restore water quality require water quality monitoring to establish baseline conditions as well as follow up monitoring and reporting to demonstrate compliance with permitted projects. Funds under this article will support town-wide marine and fresh water sampling, post-alum treatment monitoring of fresh water ponds, ongoing Lonnie’s Pond oyster efforts, Cedar Pond compliance reporting, , and consulting funds for wastewater management coordination. | Planning and Community Development | The development of the management plan us underway. The project team hosted a well attended first public comment session on June 16th. | 2025-06-23
ATM 2024 | 29 | Fund Crystal Lake Alum Treatment | 75000 | The 2021 Crystal Lake Management Plan was developed to provide an understanding of existing water quality and trends. Crystal Lake experienced an algae bloom in late 2023. The 2021 plan recommended completing an alum treatment in the lake as an interim step with a plan to sewer upgradient properties. Alum is a State accepted management strategy to maintain water quality through the summer months. The Orleans Conservation Commission issued a permit for an alum treatment in March 2024. | Planning and Community Development | Project successfully completed with no adverse impacts during or after the application to the pond. | 2025-06-23
ATM 2024 | 30 | Fund Conservation, Recreation, and Open Space Plan | 30000 | This article funds an update of the Conservation, Recreation & Open Space Plan. The plan identifies strategies and priorities for the preservation of open space and recreation. Once the new plan is certified by the MA Division of Conservation Services, the Town will be eligible to apply for reimbursement grants for open space purchases. Orleans has benefited greatly from this program in the past with several grant awards of approximately 50% of the purchase price of acquired land. Since 1982, Orleans has received $4.8M in grant funding to support 35 open space purchases. | Planning and Community Development | Open Space & Recreation Plan. Consultant hired, kickoff meeting held December 2024. A draft Open Space & Recreation Plan (OSRP) is due from the consultant in July 2025. The draft will be posted and made available for comment before being finalized and sent to the Division of Conservatin Services for approval in the Fall. | 2025-06-23
ATM 2024 | 32 | Fund 46 and 58 Eldredge Park Way Campus Study | 150000 | $150,000.00 to fund a feasibility study and related costs for the development of a multipurpose municipal campus, the focus of which will be for Fire Rescue Services, Elementary School, and Recreational/ Community facility needs. | Town Manager | The funding of this study will provide for a collaborative process between the Select Board and the Orleans Elementary School Committee towards identifying solutions for future fire/rescue station, elementary school, and recreational/community facility needs on Town owned land located at 46 and 58 Eldredge Park Way. This land currently serves as the home of the Orleans Elementary School and the Fire Department. Award to TGAS with Feasibility Study due 4/1/25. Final Report is here: https://www.town.orleans.ma.us/DocumentCenter/View/9168/Orleans-2040-Campus-Feasibility-Study-Final-Report?bidId= | 2025-06-15
ATM 2024 | 33 | Fund Village Center to Nauset Beach Multi-use Path Feasibility Study | 85000 | $85,000.00 for the purpose of funding a feasibility study for a multi-use pathway along Beach Road from Main Street to Nauset Beach. | Planning and Community Development | VHB hired to conduct feasibility study. Numerous public discussions on ideas and concepts. Engineer report due in Fall. | 2025-06-23
ATM 2024 | 34 | Skaket Beach Management Plan | 80000 | $80,000.00 to fund a beach management plan for Skaket Beach. | Department of Public Works | Project is on hold at this time as SRF financing was not available to the Town. | 2025-06-27
ATM 2024 | 35 | Fund Economic and Community Development Initiatives | 240000 | To see if the Town will vote to transfer from available funds the sum of $240,000, or any other sum, for the purpose of funding economic and community development initiatives, as determined by the Town Manager , including all costs incidental and related thereto, and further authorize the Select Board and /or Town Manager to apply for and accept any Federal, State, and County grants or other funds that may be available for this purpose, and to enter into Intermunicipal Agreements for acceptance of any such grants or funds, or to take any other action relative thereto. | Town Manager | The development of the management plan is underway. The project team hosted a well attended first public comment session on June 16th. | 2025-06-23
ATM 2024 | 36 | Fund the Redesign of the Depot Square Property | 70000 | $70,000.00 for the redesigning the Depot Square property and related costs. | Town Manager | This article will fund the design of the Depot Square property located on Old Colony Way. This location serves both residents and visitors and was studied in the past for a redesign. A consultant/ design architect will be hired to produce an actionable design that will incorporate the use of previous studies and will include a public participation component. Additionally, the design will include the potential siting of public bathrooms as previous studies have suggested. The property has potential to serve as an important stopover for users of the Cape Cod Rail Trail and will be a component of our economic success. | 2024-11-01
STM 2024 | 9 | Pickleball Development | 100000 | To see if the Town will vote to transfer from available funds the sum of $100,000, or any other sum, for the purpose of developing pickle ball courts at a location to be determined by the Select Board, or to take any other action relative thereto. (Select Board) | Recreation | The best course of action with adding additional pickleball courts, has been determined to include the courts within the Eldredge Park Renovation (Article 10). See Article 10 for additional details. | 2025-06-20
STM 2024 | 10 | Recreational Facilities and Infrastructure Design, Engineering, Repairs & Construction | 850000 | To see if the Town will vote to transfer from available funds, the sum of $850,000, or any other sum, for the purpose of design, engineering, repairs, or construction of recreational facilities and infrastructure as identified in the Town of Orleans/ Nauset Regional Middle School Master Plan in the location identified as Phase 1, and other needs and locations, including private property, as determined by the Recreation Director and the Town Manager, or to take any other action relative thereto. (Select Board) | Recreation | Since the engineering firm, Weston & Sampson, have been awarded the contract, we have had numerous meetings, including one on site. With constant communication between the Department and the engineering firm, concepts have been created. There will be a joint meeting between the Select Board and the Recreation Advisory Committee on Wednesday, July 30th where Weston & Sampson will discuss those concepts and look for feedback from SB, RAC, and the public. To date $17,380.00 has been expended. Upon completion of the joint meeting, one concept will be decided upon. | 2025-06-20
STM 2024 | 11 | Acquire Land Located at 72 Tonset Road | 2500000 | To see if the Town will vote to authorize and direct the Select Board to acquire by gift, by purchase, by eminent domain or otherwise, for general municipal purposes the land, together with the improvements thereon, located at 72 Tonset Road, Orleans, MA and shown on the Town of Orleans Assessor’s Map 34 as Parcel 37 and containing an area of 2.21 acres, more or less, and described in a deed recorded with the Barnstable County Registry of Deeds in Book 30646 Page 339; and to raise and appropriate or transfer from available funds the sum of two-million five hundred thousand ($2,500,000.00) Dollars for such acquisition; provided that such land shall be under the control of the Select Board for general municipal purposes, and, further, to authorize the Select Board to purchase of the land and to execute any and all instruments as may be necessary on behalf of the Town, or to take any other action relative thereto. (Select Board) | Town Manager | Parking spaces, walking trails, and a kayak rack were added in Spring 2025. A task force will be established, and a Request for Qualifications (RFQ) is forthcoming to help identify potential future uses of the property, with a focus on exploring natural connections to the adjacent Town-owned parcel at 82 Tonset Road. | 2025-06-20
STM 2024 | 12 | Climate, Sustainability, and Environmental Action Funding | 100000 | To se if the Town will vote to transfer from available funds, $100,000, or any other sum for the purpose of funding climate, sustainability, and environmental action in the Town of Orleans, or to take any other action relative thereto. (Select Board) | Town Manager | These funds will be used to contract with a consultant to establish a climate action roadmap that is specific to the Town of Orleans. We understand climate change is a threat to us locally, regionally, and beyond. Having a local climate action roadmap for all community members will play a critical role in our resilience to the impacts of climate change and will ensure we are being a partner in working together towards the climate goals set forth by the Commonwealth. The actions established by this roadmap will be trackable, and we will see the progress we are all making as a community going forward. Additionally, the funds will provide potential grant matches for climate/sustainability/environmental related grant applications and implementation of actions as prescribed by the climate action roadmap. | 2024-11-01
STM 2024 | 13 | Fund HVAC Improvements for the Water Treatment Facility | 148000 | To see if the Town will vote to transfer from available funds the sum of $148,000, or any other sum, for the purpose of funding HVAC improvements at the Orleans Water Treatment Facility, or to take any action relative thereto. (Select Board) | Department of Public Works | Bid awarded to G&H Heating & Cooling in the amount of $354,512.00. Project is currently on hold till approximately November/December 2025 due to a Nationwide backorder of refrigerant. | 2025-06-27
STM 2024 | 14 | OES Stabilization Fund-Special Education | 86000 | To see if the Town will vote to transfer the sum of $86,000 from available funds to the Special Education Stabilization Fund, or to take any other action relative thereto. (Select Board) | Town Manager | This article provides funding to the special education stabilization fund. | 2024-11-01
STM 2024 | 15 | Fund Conservation Fund | 85000 | To see if the Town will vote to transfer from available funds the sum of $85,000, or any other sum, to the Conservation Fund, or to take any action relative thereto. | Planning and Community Development | Conservation Fund allocation. | 2024-11-01
STM 2024 | 19 | Fund NW School House Restoration Project (CPC) | 11000 | To see if the Town will vote to appropriate $11,000 from the Community Preservation Fund for the purposed of funding the NW School House Restoration project as approved and recommended by the Orleans Community Preservation Committee, or to take any other action relative thereto. (Community Preservation Committee) | Community Preservation Committee | This grant is to cover the increase in electrical costs for installation of new kitchen equipment and has not yet completed. The funds will be encumbered. | 2025-06-24
STM 2024 | 20 | Fund Affordable Housing Trust | 500000 | To see if the Town will vote to transfer from available funds the sum of $500,000, or any other sum, to be deposited in the Affordable Housing Trust Fund, or to take any other action relative thereto. (Select Board) | Planning and Community Development | Funds have been used to support various activities of the Trust, including a rental assistance program, housing project developments at 22 Old Tote Road, Governor Prence site | 2025-06-23
STM 2024 | 21 | Orleans Housing Initiatives | 500000 | To see if the Town will vote to raise and appropriate or transfer from available funds the sum of $500,000, or any other sum for the purpose of funding housing initiatives as determined by the Town Manager, or to take any other action relative thereto. (Select Board) | Planning and Community Development | Year-Round rental incentive program (aka Lease to Locals) will launch August 2025. ADU/HMLP incentive program will launch July 15. Short-term rental monitoring program ongoing. | 2025-06-23
STM 2024 | 22 | Fund Boland Pond Management Plan | 55000 | To see if the Town will vote to transfer from available funds the sum of $55,000, or any other sum, for the purpose of funding a Boland Pond management plan, or to take any other action relative thereto. (Select Board) | Planning and Community Development | Project is underway with sampling, analysis and environmental assessments per scope of services. With Phase 2 funding approved in May 2025, project will proceed to completion in early 2026. | 2025-06-23
Select Board Project | n/a | 44 Main Street | n/a | The Orleans Community Building at 44 Main Street is a 3,848-square-foot facility that was built in 1935 and operated as a Fire House until the late 1950's. The mission of the Orleans Community Building is to provide occasional, temporary indoor and/or outdoor space for local non-profit, civic, and public organizations and Orleans residents (year-round residents and nonresident taxpayers) to engage in recreational, social, educational, cultural, community service, civic, and governmental activities. The Orleans Community Building provides opportunities for people of all ages to participate in a wide range of legally permitted activities and programs that enrich, educate, foster support, and enhance the Town of Orleans community, and promote mental and physical well-being. | Planning and Community Development | Received cost estimate for mixed-use reconstruction of building. Pursing public/private approach to redevelopment. Drafting RFP for long-term lease of building, while maintaining first-floor community space. | 2025-06-23
Select Board Project | n/a | Staples Plaza Crosswalk (Route 6A) | n/a | Connect Trove to Staples Plaza; crosswalk across Route 6A | Department of Public Works | No progress from DOT to date. Town is working to get the request included on MassDOT's Vulnerable Road User (VRU) Improvements at Municipal Bus Stops program. | 2025-06-27
Select Board Project | n/a | Kent's Point | n/a | This 27.7-acre salt waterfront parcel was purchased by the Town in 1988. The area includes wooded upland, coastal banks, salt marsh, and a small area of sandy beach. Nearly surrounded by salt-water bodies, you can enjoy views of Frost Fish Cove, The River, and Lonnie’s Pond. | Planning and Community Development | Project is on hold at this time. | 2025-06-23
Select Board Project | n/a | Pollinator Pathway Resolution | n/a | Orleans will set an example by seeking to adopt the pollinator-friendly practices listed below on town-owned land, and encouraging property owners, residents, business owners, and land trusts to adopt pollinator-friendly practices on their properties that: * Plant more native plant species, especially those that provide forage for pollinators; * Avoid the use of insecticides, fungicides, and herbicides for aesthetics; and do not plant flowering plants treated with systemic insecticides or use seeds coated with systemic neonicotinoids; *Reduce area dedicated to managed turf lawns, converting this area to pollinator friendly planting when possible; and adopt organic or chemical-free lawn and landscaping practices, including allowing plant stalks, seed heads and fallen leaves and pine needles to remain through fall and winter, when possible, to provide habitat, food for birds, soil nourishment, and to give important protection needed by overwintering pollinators. | Town Manager | A non-binding resolution endorsing the protection of pollinators and enhancement of pollinator habitat. See: https://www.town.orleans.ma.us/DocumentCenter/View/2819/Orleans-Pollinator-Pathway-Resolution-PDF
Select Board Project | n/a | Green Community | n/a | Orleans was designated a Green Community by the MA Department of Energy Resources (DOER) on December 27, 2018. | Town Manager
Select Board Project | n/a | Fertilizer Home Rule Petition 2022 | n/a | The Orleans Select Board voted unanimously on June 15, 2022 to take action in addressing clean and healthy waters in Orleans, protecting our environment, wildlife, residents, visitors, pets, economy and property values by supporting a Home Rule Petition: An Act of Prohibiting the Application of Fertilizer in the Town of Orleans. We thank you for your support of the Petition at the October 17, 2022 Fall Town Meeting, which is now Bill H.874 at the State Legislature, and was reported favorably by the Committee on Environment and Natural Resources on 3/21/2024. | Town Manager | Fertilizer Bill H.1573 have been refiled in the legislative session by Senator Cyr and Representative Luddy. This petition was developed from Nantucket’s, and similar initiatives are being considered by other Barnstable County communities/towns as well. See: town.orleans.ma.us/1109/Fertilizer-Home-Rule-Petition-2022 | 2025-06-01
Select Board Project | n/a | Pesticide Home Rule Petition 2023 | n/a | The Orleans Pesticide Home Rule Petition, passed at the Fall Town Meeting October 16, 2023 and now Bill H.4481 at the Statehouse will be considered by The Joint Committee of Environment and Natural Resources. The Petition’s purpose is to “reduce toxic pesticide use in and on public and private property in the Town of Orleans in order to promote a healthy environment and to protect the public from the hazards of pesticides and for implementation of sustainable land and building management practices on all public and private property.” | Town Manager | Pesticides Bill H.1574 have been refiled in the legislative session by Senator Cyr and Representative Luddy. ThePesticide petition has also been voted by Eastham and Wellfleet, and similar initiatives are being considered by other Barnstable County communities/towns as well. There is a growing trend of reducing toxic chemicals in the food system (Red Dye #3) and environment. See: town.orleans.ma.us/1335/Pesticide-Home-Rule-Petition-2023 There is also a link below to the Pesticide petition with 4,300+ support signatures so far Petition Change.org - https://www.change.org/p/protect-our-environment-reduce-pesticide-use-in-orleans-ma | 2025-06-01
Select Board Project | n/a | Nauset Estuary Dredging | n/a | Location: Channel from Town Cove to behind the barrier beach and stopping at the Nauset Inlet | Department of Public Works | Project is on hold at this time. | 2025-06-27
Select Board Project | n/a | 66 & 76 Route 6A | n/a | The Town awarded the redevelopment opportunity to Preservation of Affordable Housing (POAH), Housing Assistance Corporation, and Habitat of Humanity of Cape Cod. The proposal includes 78 units of mixed-income, mixed-tenure housing and supporting site improvements. | Planning and Community Development | Project is on hold at this time. | 2024-11-01
Select Board Project | n/a | 19 West Road | n/a | A multi-family rental development of 62 units, the project renovates the building on West Road (next to Skaket Corners) previously occupied by Cape Cod Five’s Operations Center. The developer Pennrose secured approval for a comprehensive permit from the Orleans Zoning Board of Appeals, for federal and state tax credit financing by Massachusetts Department of Housing and Community Development (DHCD), for contributions from all eight towns on the Lower and Outer Cape, and gap financing in the form of a $2 million bond from the Town of Orleans’ Community Preservation Committee. Demolition and construction started in December 2023 and is expected to be completed in 2025. For inquiries about the availability of these units, use the Contact Us form at: https://www.pennrose.com/apartments/massachusetts/cape-cod-five/ | Planning and Community Development | 62-unit project moved in first tenants in early June. TCOs and substantial completion in May - completing final punchlist items. Lottery complete and waiting list open. Of lottery applicants, 53% qualified for local preference; 58% qualified for one-bedrooms units. | 2025-06-23
Select Board Project | n/a | 107 Main Street | n/a | The property for a new 14-unit development at the site of the former Mason’s Lodge on Main Street was acquired by the Orleans Affordable Housing Trust Fund in 2021. An agreement with the Housing Assistance Corporation (HAC) was approved to develop the project, following a Request for Proposals process. HAC secured approval of the Orleans Zoning Board of Appeals, as well as State grants and necessary financing. Financial closing occurred in July 2024, following immediately by start of construction. | Planning and Community Development | 14-unit project is accepting applications for the lottery. Construction scheduled for completion in October. | 2025-06-23
Select Board Project | n/a | Native Planting Policy | n/a | The purpose of this policy is to continue evolving our dedication to the environment, including the Pollinator-Friendly Resolution (January 19, 2022), by promoting a predominance of native plant species on Town-owned properties for the purpose of building resilient landscapes and increasing biodiversity in a changing climate. This policy is intended to support pollinator species and other native wildlife and help maintain and enhance the Town of Orleans’ living green infrastructure. | Town Manager | See: town.orleans.ma.us/DocumentCenter/View/9097 (pages 29-37) for the approved policy. | 2025-05-25
ATM 2025 | 12 | Fund the Design of a New Fire-Rescue Station | 4500000 | A new facility would address longstanding deficiencies in the current building, which no longer meets the safety standards, operational demands, or space requirements of today’s — or tomorrow’s — fire-rescue services. Built in 1987, the existing station is undersized and outdated. It lacks appropriate facilities for decontamination, training, and adequate housing for personnel and apparatus. As call volumes rise and building codes evolve, the Town’s ability to provide effective and timely emergency response depends on modernizing this critical facility. | Town Manager | Owner's Project Manager RFQ issued on June 23. Building Committee interviews scheduled for June 25. | 2025-06-20
ATM 2025 | 20 | Orleans Solar Development | 5000000 | This article will fund the development of municipally owned solar projects at 3 potential locations in town. This article was placed on the warrant while the RFP process is underway. The proposals are due back to the Town by May 1st. The Select Board and staff will be working to decide on a path forward based on the results of the RFP. Should the Select Board decide to move forward with an ownership option for these solar photovoltaic facilities, a presentation will be made to Town Meeting with the applicable supporting information. The number of $5,000,000 is a place holder amount and is subject to change to a lower number in the final motion. | Town Manager | RFP issued on 7/9 and scheduled to close on 8/15/25. | 2025-06-20
ATM 2025 | 21 | Town Cove Bulkhead Replacement | 1600000 | This project provides funds for the construction of the replacement of the easterly bulkhead located at the Goose Hummock town landing on Town Cove. This landing receives heavy commercial and recreational use from April to December annually. In 2018, a marine engineering firm was contracted by the Town to perform topside and underwater inspections of the eastern timber bulkhead at Goose Hummock town landing. At that time, it was recommended that this section of bulkhead be replaced within 5 years to prevent continued loss of backfill and to remove the load restriction that was imposed due to compromised structural integrity. Design and permitting was funded in 2022 and has been completed. | Department of Public Works | Construction bid documents are being prepared for release in July/August. It is anticipated that construction will take place over Winter 25/26. | 2025-06-27
ATM 2025 | 22 | Fund FY26 Community Preservation program budget | 1363232 | The Community Preservation Committee recommends that the following amounts be appropriated and/or reserved from Fiscal Year 2026 Community Preservation Fund revenues and funds from the Toop Family Fund, unless otherwise specified, for Fiscal Year FY2026 community preservation purposes with each item considered a separate appropriation. Revenue is based on available funds ($30,709), a 3% surtax ($1,256,736), an annual Toop grant of ($3,083), and an anticipated “match” from the State of Massachusetts ($170,702). State law requires that at least 10% of Community Preservation funds be expended or reserved for Historic Preservation, Open Space/Recreation, and Community Housing. This article meets those requirements and funds important projects in each area: Historic Preservation: $523,280 (35.81%) Open Space/Recreation $281,425 (19.26%) Community Housing: $523,027 (35.79%) | Community Preservation Committee | No grants have been notified and no projects will begin until the start of FY2026. | 2025-06-24
ATM 2025 | 23 | CWRMP Implementation Phase III Lakes and Ponds Sewer Area- Construction | 40500000 | Article 23 funds construction for the Phase 3 Lakes and Ponds Sewer Area Project, the next phase of the sewer system expansion identified in the Amended Comprehensive Wastewater Management Plan. Phase 3 Lakes and Ponds Sewer Area is critical to meeting the Town’s water quality objectives for its lakes, ponds, and embayments as well as maintaining compliance with the Pleasant Bay Watershed Permit. The Permit allows the Town to strategically implement improvements in lieu of passing new Title V requirements to individual property owners. Phase 3 Lakes and Ponds Sewer Area is also included in the State’s 2025 Intended Use Plan for the Clean Water State Revolving Fund (SRF), which makes it eligible for subsidized financing. MassDEP determined that the Phase 1 and Phase 2 projects qualified for 0% interest rate loans and the Town anticipates that the Phase 3 project will have the same determination. SRF requires a construction appropriation to continue with the financing application and passage of Article 23 and subsequent exemption vote will meet this requirement. This project is also eligible for financial assistance up to 25% from the Cape and Islands Water Protection Fund. | Department of Public Works | Design is entering into final phase, construction is not anticipated to begin until Fall/2026. | 2025-06-27
ATM 2025 | 24 | CWRMP Implementation Phase II Meetinghouse Pond Area- Connection Engineering Services | 600000 | DPW requests funding for AECOM engineering services to engage, respond to, and directly collaborate with Phase II property owners, including engineers and contractors, to facilitate individual property connections in the Meetinghouse Pond Area Phase. | Department of Public Works | Drawdown of funding is not expected to begin until a notice to connect is issued to phase II users later this year. | 2025-06-27
ATM 2025 | 25 | Fund Water Quality Testing | 122500 | Town programs to protect and restore water quality require monitoring to establish baseline conditions as well as follow up monitoring and reporting to demonstrate compliance for permitted projects. Funds under this article will support town-wide marine and freshwater sampling, Cedar Pond compliance monitoring, ongoing Lonnie's Pond oyster efforts, completion of the Boland Pond management plan. | Planning and Community Development | FY26 funds to be used in accordance with the article | 2025-06-23
ATM 2025 | 26 | Mill Pond Nitrogen Management Evaluation | 125000 | Mill Pond in the Nauset Estuary suffers from seasonal anoxic conditions and degraded habitat. The purpose of this evaluation is to determine short-term actions to improve water quality, knowing that actions currently identified in the Town’s Amended CWRMP are many years away. Mill Pond sewers are currently scheduled for Phase 11 of the Town’s 16-phase sewer program. A series of tasks will evaluate alternatives that can be implemented in the short-term and later integrated into the Town’s long-term wastewater management strategy. The intent of this scope of work is to identify projects that are likely, based on available information, to be feasible and to most cost-effectively yield faster water quality improvements in Mill Pond. | Planning and Community Development | Evaluation of alternatives under way with AECOM and Wright-Pierce. Project is being overseen by the WMAC. Expected final report by end of calendar year. | 2025-06-23
ATM 2025 | 27 | Orleans Retail Cannabis Courier Services | n/a | This article will align Orleans Zoning (Chapter 164) with the current Massachusetts Cannabis Control Commission (the "CCC") regulations. In April 2024, the CCC updated their model Host Community Agreement to allow for currently licensed Marijuana Retailers to apply for, obtain, and operate a license as a Marijuana Courier within the Municipality. The number of Marijuana Retailers in Orleans shall remain limited to two (2) establishments. | Planning and Community Development | Bylaw amendment under review by Attorney General's office. | 2025-06-23
ATM 2025 | 28 | Amend General Bylaw Chapter 104 - Affordable Housing Trust Definition of Moderate Income Housing to 120% AMI | n/a | This article seeks to clarify that ‘low- and moderate-income’ as it applies to current and future Affordable Housing Trust funds will be defined as housing for the benefit of households or individuals earning up to 120% of the HUD Area Median Income. The state statute enabling affordable housing trusts (Massachusetts General Laws, Chapter 44, §55C) does not define the terms “low and moderate income”. Communities may do so based on their residents’ local economic conditions and housing needs. The incomeeligibility for CPA funds for "community housing" remains capped at 100% AMI. This article only applies to funds from non-CPA sources. | Planning and Community Development | Bylaw amendment under review by Attorney General's office. | 2025-06-23
ATM 2025 | 29 | Amend General Bylaw Chapter 106 - Demolition of Historical Structure - Appeals to Select Board | n/a | This article amends the process for appealing the decision of the historic commission on the demolition delay bylaw. If adopted any appeal would need to be filed in a Court of competent jurisdiction rather than with the Select Board. | Town Manager | Department is following regulation promulgation by Seasonal Communities Working Group; Public listening sessions scheduled for summer. Regulations anticipated Sept-October. | 2025-06-23
ATM 2025 | 30 | Amend General Bylaw Chapter 40- Personnel | n/a | This article will amend language in the personnel bylaw for the compensation plans, vacation language, health insurance and Child Care, Recreational and Personal Development Class Reimbursements. These adjustments align with what has been negotiated with the Town Unions and we are seeking to align similar benefits for our nonunion employees. These changes have been reviewed and supported by the Personnel Advisory Board. | Town Manager
ATM 2025 | 31 | Accept MGL Ch. 59 § 5 Cl. 22I - Property, Exemptions- Increase Disabled Veteran Exemption | 0 | Acceptance of this local option will double the tax exemption amounts awarded to disabled veterans and their surviving spouses who use their Orleans home as their primary residence. These amounts have been in place since Clause 22 was originally passed. With the passage of 2024's HERO Act, these amounts have been increased for the first time. We currently have 41 veteran-owned properties that would benefit. The $21,800 needed to cover the increased exemptions for these disabled veterans would come from our annual statutory contribution to the overlay reserve. | Assessing | The increased award amounts are updated on the town website, in all town literature, in our CAMA software, and in MUNIS. Last year's recipients will receive new applications for their FY2026 exemption applications in their mail by July 1, 2025. The new award amounts will be appear on the Q3/Q4 tax bills that go out in December 2025. | 2025-06-20
ATM 2025 | 32 | Acceptance of the Massachusetts General Law: Seasonal Community Designation | n/a | This article asks voters to accept the Seasonal Community Designation under Massachusetts General Laws Chapter 23B, Section 32(b), which formally recognizes Orleans as a seasonal community where the population significantly increases in the summer. Accepting this designation makes the town eligible for state resources, grants, and funding opportunities tailored to seasonal communities. This assists in supporting infrastructure needs, emergency services, and workforce housing needs. It also strengthens Orleans’ ability to address the unique challenges of a fluctuating population, including increased demand on municipal services. This designation does not impose new regulations or restrictions on residents or businesses. | Planning and Community Development | Department is following regulation promulgation by Seasonal Communities Working Group; Public listening sessions scheduled for summer. Regulations anticipated Sept-October. | 2025-06-23